## Sheet1
Christmas Campaign Timeline Planner
unSeminary
Today's Date: | 2013-06-19 | Days Until Christmas: | 188
Last Sunday of the Year: | 2013-12-29 | Days Until Year End: | 195
Christmas Eve: | 2013-12-24
Year End: | 2013-12-31
Activity | Start Date | End Date
Campaign Leadership Defined | 2013-06-02 | 2013-06-16
Campaign Research & Planning Phase | 2013-06-16 | 2013-07-07
Initial Campaign Definition Proposal | 2013-07-07 | 2013-07-21
Small Group Tour Booking | 2013-08-11 | 2013-08-18
Invitations to Leadership Event | 2013-08-11 | 2013-08-18
Finalization of Case for Cause | 2013-07-28 | 2013-08-18
Leadership Event | 2013-09-08 | 2013-09-22
Leadership Reminder Mailing | 2013-09-29 | 2013-10-06
Small Group Tour | 2013-10-13 | 2013-11-10
Sunday Morning Launch | 2013-11-17 | 2013-11-24
Direct Mailing Arrives at All Donors Homes | 2013-11-17 | 2013-11-24
Sunday Morning Example Videos | 2013-12-01 | 2013-12-29
Year End Gift Email Reminder | 2013-12-27 | 2013-12-29
Initial Thank You Annoucement | 2014-01-12 | 2014-01-12
Thank You Mailing Development | 2013-12-22 | 2014-01-12
Final Annoucement | 2014-01-19 | 2014-01-26
Leadership Campaign Debrief | 2014-02-09 | 2014-02-23
Formulas:
Start Date = [End Date]-(7*2)
Start Date = [Start Date, row below]
End Date = [Start Date, row below]
End Date = [End Date, row below]
Note on B5: Change this to the last Sunday that you plan on hosting public services. -Rich Birch